CAMPAIGN PLAN

VisionPath

Pre-Launch Waitlist Campaign

Budget: $250/month  |  Timeline: 8 weeks  |  Goal: 500 waitlist signups

Prepared February 2026

# 1. Executive Summary

VisionPath is an AI-powered visual project planning tool that lets founders describe their idea and get a complete project plan rendered as an interactive node graph on an infinite canvas. Unlike Lovable or Bolt, which generate UI prototypes without real backend architecture, VisionPath produces a structured plan with goals, features, tasks, PRDs, implementation prompts, and typed dependencies that you can see, navigate, and refine all at once.

This campaign will drive 500 waitlist signups over 8 weeks on a $250/month budget by targeting non-technical startup founders on the channels where they already hang out: X/Twitter, Reddit, Indie Hackers, and Product Hunt. The core message is simple: stop planning blind, see your entire project before writing a single line of code.

# 2. Campaign Objective

SMART Goal: Generate 500 waitlist email signups from startup founders and non-technical builders within 8 weeks of campaign launch, with a target cost-per-signup of $1 or less.

# 3. Target Audience

## Primary: Non-Technical Startup Founders

First-time or repeat founders who have an app idea but need help translating it into a structured development plan. They may use no-code tools, hire developers, or use AI coding assistants. They feel overwhelmed by the gap between their idea and a real product.

### Audience Profile

| Attribute | Detail |
| --- | --- |
| Role | Startup founder, solopreneur, aspiring builder |
| Pain Point | Has an idea but no structured way to plan it. Feels lost between idea and execution. |
| Current Tools | Notion, Google Docs, Lovable, Bolt, ChatGPT for brainstorming |
| Desired Outcome | A visual, complete project plan they can hand to developers or feed to AI coding tools |
| Discovery Channels | X/Twitter, Reddit (r/startups, r/SideProject), Indie Hackers, Product Hunt, YouTube |
| Buying Stage | Problem-aware. Knows planning is messy, hasn't found the right tool yet. |

# 4. Positioning & Messaging

## Core Positioning Statement

VisionPath is the first AI project planner that shows your entire product as a visual map. Describe your idea, get a complete plan with goals, features, tasks, and dependencies on an infinite canvas. Design and prototype with a real architecture underneath, not just pretty mockups.

## Message Hierarchy

| Layer | Message |
| --- | --- |
| Hook | "Stop planning blind. See your entire project before you write a line of code." |
| Problem | Founders waste weeks going back and forth in docs and chat with AI. They still can't see how everything connects. |
| Solution | VisionPath turns your idea into a visual DAG of goals, features, and tasks. AI generates the plan; you refine it on an infinite canvas. |
| Differentiator | Unlike Lovable/Bolt that produce throwaway prototypes, VisionPath gives you the architecture: PRDs, implementation prompts, typed dependencies, and exportable plans for Cursor, Claude, or your dev team. |
| CTA | "Join the waitlist. Be the first to plan visually." |

## Supporting Proof Points

- 7 views of the same project: Canvas, List, Table, Board, Timeline, Sprints, and Pages

- AI generates PRDs and implementation prompts you can paste directly into Cursor or VS Code

- Typed dependency edges with blast radius analysis: see exactly what breaks if something slips

- Export to .cursorrules, CLAUDE.md, or Markdown so your plan flows directly into your dev workflow

# 5. Channel Strategy

With a $250/month budget, the strategy is overwhelmingly organic with small, targeted paid boosts. Every dollar should amplify content that's already getting organic traction.

| Channel | Tactic | Content Type | Budget | Goal |
| --- | --- | --- | --- | --- |
| X / Twitter | Build in public thread series, demo GIFs, engagement with founder community | Short-form video, GIF walkthroughs, threads, quote tweets | $50/mo boost | 200 signups |
| Reddit | Genuinely helpful posts in r/startups, r/SideProject, r/EntrepreneurRideAlong | "I built this" posts with context, demo links, honest progress updates | $0 (organic) | 100 signups |
| Indie Hackers | Product page, milestone posts, engagement in groups | Build log, revenue/growth updates, lessons learned | $0 (organic) | 50 signups |
| Product Hunt | Launch day campaign (time for Week 6-7) | Product page, maker story, demo video | $100 (assets) | 100 signups |
| YouTube / Loom | 2-3 min demo videos showing the canvas in action | "Watch me plan a SaaS in 2 minutes" walkthrough | $0 (organic) | 50 signups |
| Email (collected) | Weekly build update to waitlist subscribers | Progress updates, sneak peeks, launch countdown | $0 (free tier) | Retention |

# 6. Content Calendar (8-Week Sprint)

## Weeks 1-2: Foundation

Theme: Establish presence and start the build-in-public narrative.

- Set up VisionPath X/Twitter account with pinned demo GIF and waitlist link in bio

- Create Indie Hackers product page with build story

- Post first "build in public" thread on X: "I'm building the project planner I wish existed as a non-technical founder"

- Record first 90-second demo video: "Describe an idea, watch it become a visual plan"

- Set up email capture (Buttondown, Loops, or Mailchimp free tier) connected to landing page

- First Reddit post in r/SideProject: share the problem you're solving, ask for feedback

## Weeks 3-4: Traction

Theme: Show the product in action, build social proof.

- Post 3x/week on X with demo GIFs: canvas navigation, AI plan generation, blast radius view

- Boost top-performing X post ($25)

- Reddit post in r/startups: "Here's how I plan every project now" with walkthrough

- Publish comparison thread: "VisionPath vs Lovable vs Bolt: what's actually different"

- Send first waitlist email update: "Here's what we built this week" + sneak peek

- Record second video: "I planned an entire SaaS with AI in 5 minutes" (YouTube + X)

## Weeks 5-6: Momentum

Theme: Amplify, gather testimonials, prep for Product Hunt.

- Launch early access to 20 waitlist subscribers for feedback and testimonials

- Post testimonial screenshots and user plan examples on X

- Boost second high-performing X post ($25)

- Indie Hackers milestone post: waitlist count + key learnings

- Prep Product Hunt assets: product description, tagline, maker comment, 4 screenshots, demo video

- Line up 10 friends/supporters to upvote on PH launch day

## Weeks 7-8: Launch

Theme: Product Hunt launch + full push across all channels.

- Launch on Product Hunt (Tuesday or Wednesday, 12:01 AM PT)

- Same-day X thread: the story behind VisionPath, link to PH

- Reddit post in r/startups and r/SideProject with PH link

- Email entire waitlist: "We just launched on Product Hunt"

- Post-launch: share results, thank supporters, keep momentum with daily X posts for 5 days

- Retarget PH visitors with boosted X post ($50 remaining budget)

# 7. Budget Breakdown

Total 8-week budget: $500 ($250/month x 2 months)

| Line Item | Cost | Notes |
| --- | --- | --- |
| X/Twitter post boosts | $100 | $25/boost x 4 top-performing posts |
| Product Hunt launch assets | $100 | Video editing, screenshot polish, Canva Pro |
| PH launch day retargeting boost | $50 | Boost the launch announcement post on X |
| Email tool (free tier) | $0 | Buttondown/Loops free for <1000 subscribers |
| Screen recording (Loom) | $0 | Free tier sufficient for demo videos |
| Contingency / opportunistic spend | $250 | Reddit ads test, additional X boosts, or save for month 3 |
| TOTAL | $500 | $250/month over 2 months |

# 8. Success Metrics & KPIs

| Metric | Week 2 Target | Week 4 Target | Week 8 Target |
| --- | --- | --- | --- |
| Waitlist signups | 50 | 150 | 500 |
| Landing page visitors | 500 | 2,000 | 5,000+ |
| X/Twitter followers | 100 | 300 | 750+ |
| Landing page conversion rate | 8% | 10% | 10%+ |
| Email open rate | N/A | 40%+ | 35%+ |
| Cost per signup | < $2 | < $1.50 | < $1 |

# 9. Key Content to Create

## Must-Have Assets (Week 1)

- 30-second GIF: type an idea, watch the canvas populate with a full plan

- Landing page waitlist form (email capture with clear value prop above the fold)

- X/Twitter bio + pinned post with demo GIF and waitlist link

- Indie Hackers product page with builder story

## High-Impact Content (Weeks 2-4)

- "VisionPath vs Lovable vs Bolt" comparison thread: focus on real code architecture vs throwaway prototypes

- 90-second demo video: "Plan a SaaS from scratch in under 2 minutes"

- "Build in public" weekly thread series: honest progress, user count, lessons

- Feature spotlight GIFs: blast radius analysis, 7-view switcher, AI plan generation, export to Cursor

## Launch Assets (Week 6)

- Product Hunt page: tagline, description, 4 polished screenshots, 60-second product video

- Maker story post for PH: "Why I built VisionPath"

- Launch day email to waitlist with PH link and ask for support

# 10. Landing Page Optimization

Your current landing page at planner-ruby-seven.vercel.app has a strong foundation. Here are specific changes to maximize waitlist conversions:

## Above the Fold (Critical)

- Replace "What are you building?" with a stronger hook: "See your entire project before you code a single line"

- Add a prominent email signup form directly below the headline, not just "Try It Free"

- Add a 15-second auto-playing demo GIF showing: type idea, canvas populates, click through views

- Add social proof: "Join 200+ founders planning visually" (update the number as it grows)

## Messaging Changes

- Lead with the outcome ("Visual project plans in 60 seconds"), not the feature ("AI-powered planning")

- Add a comparison section: "Unlike Lovable and Bolt, VisionPath gives you the architecture, not just the mockup"

- Add an "Export to your tools" section showing Cursor, Claude, VS Code logos with one-click export messaging

## Conversion Optimizations

- Sticky CTA bar at the top that follows scroll: "Join the waitlist" with email input

- Add exit-intent popup with email capture on desktop

- Reduce the page to 3 sections: Hero + Demo, Features, CTA. Remove anything that creates decision fatigue.

# 11. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Low Reddit engagement (posts get buried) | Miss 100 signup target from Reddit | Focus on genuinely helpful posts. Engage in comments for 1 hour before/after posting. Test different subreddits. |
| Product Hunt launch underperforms | Miss 100 signup target from PH | Line up 20+ early supporters. Have killer screenshots and video ready. Post maker comment immediately. |
| Landing page converts below 5% | Need 2x more traffic to hit targets | A/B test headlines in Week 2. Add demo GIF above fold. Simplify the page ruthlessly. |
| "Lovable/Bolt comparison" messaging backfires | Perceived as negative or desperate | Frame as "different category" not "better than." Focus on what VisionPath uniquely offers, not what others lack. |

# 12. Immediate Next Steps

Week 1 priority actions to execute this plan:

- Add email capture form to landing page (Buttondown or Loops integration)

- Update landing page headline and add demo GIF above the fold

- Create VisionPath X/Twitter account with pinned demo post

- Record first 90-second screen recording of the canvas in action

- Write and schedule first "build in public" X thread for Week 1

- Create Indie Hackers product page